## Sheet1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Niyonzima Stecie | Data Collection,Model Implementation, Model Evaluation, Analysis & Reflection | n.stecie@alustudent.com
Keza Peace | Data Collection, Feature Extraction, Report Writing | p.keza@alustudent.com
Task Allocation and Tracker
# | Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
1 | Data Collection | Niyonzima Stecie, Keza Peace | 2026-02-25 | Completed | Yes | 4 activities via Sensor Logger; 52 samples; rates harmonised; saved as .csv
2 | Feature Extraction | Keza Peace | 2026-02-28 | Completed | Yes | 50-sample windows, 50% overlap; 14 features; ax–ay key; scaled + PCA
3 | Define Model Components | Keza Peace | 2026-03-02 | Completed | Yes | 4 hidden states; uniform init probs; self-loop transitions; reviewed by both
4 | Model Implementation | Niyonzima Stecie | 2026-03-04 | Completed | Yes | Gaussian HMM per class; Baum–Welch <80 iters; Viterbi applied; strong diagonal
5 | Model Evaluation | Niyonzima Stecie | 2026-03-04 | Completed | Yes | Outdoor session; 89% accuracy; still & standing >92%; jumping lowest specificity
6 | Analysis & Reflection | Niyonzima Stecie | 2026-03-05 | Completed | Yes | Still vs. standing most confused; transitions realistic; noise partly resolved
7 | Report and Team task sheet | Keza Peace | 2026-03-06 | Completed | Yes
8 | Submission | Niyonzima Stecie | 2026-03-07 | Completed | Yes
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-03-25 | Project Kickoff | N/A | Stecie, Peace | Reviewed assignment brief. Agreed on dataset collection approach, sensors to use, and target activities. Divided tasks based on strengths. | Each member to collect data independently then merge. Stecie to begin reading hmmlearn documentation. | Both members attended. Good alignment on project direction from the start.
2026-03-01 | Data & Features Review | N/A | Stecie, Peace | Peace presented collected dataset and extracted features. Reviewed feature distributions across activities. Identified ax–ay correlation as a strong discriminative feature. | Stecie to begin HMM model setup. Peace to finalise feature scaling and PCA step. | Feature visualisations were shared and reviewed together. Minor inconsistency in sampling rate resolved.
2026-03-05 | Model Review & Evaluation | N/A | Stecie, Peace | Stecie demonstrated trained HMM and Viterbi decoded sequences. Reviewed confusion matrix and evaluation metrics together. Discussed performance on unseen data. | Peace to write up Sections 1, 2 and 6 of the report. Stecie to finalise Sections 3, 4 and 5. | Model performance exceeded expectations. Both members agreed on final evaluation results before submission.
2026-03-07 | Submission | N/A | Stecie, Peace | Decide Stecie to submit | She did an amazing job.